| Work-based Learning Pathway |  |  |  |
| --- | --- | --- | --- |
| Learner name | Jonas Flynn | Role | Stage Hand |
| Workplace Brief description | StarRider Productions (Live Productions Division) Workplace includes the head office and warehouse where all the equipment is stored and maintained and the venue for where each function is held. These can often be busy environments and depending on the demands of the job, the client and the complexity of the production there is often little time for “mucking about”. This will need to be taken into account with the learning plan – while Jonas' learning is important “the show must go on” even if it is at the expense of Jonas practising a skill. |  |  |
| Facilitator | Marcelle Wyatt | Supervisor | Rod Logan |
| Overall objectives | StarRider have expanded into the corporate events production area and need additional skilled staff to take small set-ups of audio/visual (A/V) production equipment (“rig”) to client functions, set them up and ensure a great show and happy client. Jonas has expressed a keen interest in taking on more responsibilities and StarRider prefer to promote from within where possible instead of hiring new staff. At the completion of this Learning Pathway Jonas must be able to demonstrate that he can: - Set up a small A/V rig correctly, quickly and confidently - Operate the equipment correctly - Take down a small A/V rig correctly and efficiently, ensuring a neat and tidy pack-up - Load the van correctly and safely and drive to and from the venue - Be confident, polite, professional and courteous to clients and dress appropriately Ideally StarRider Productions need Jonas ready for the busy October-January season so there are 10 weeks in which to achieve these objectives. |  |  |
| WHS considerations Of training in the workplace | - Trips and falls from cables - Drunk/disorderly or abusive patrons - Electric shock - Fall from heights rigging lights, speakers etc. - Injury from Heavy Lifting - Skin-pinch injuries from closing roadcases or stands - Fatigue - Hearing damage - Spilled drinks causing either slips/fall injuries or electric shock if near power outlets - Burns if using older style Par lighting |  |  |
| Learning characteristics Including learning style | Jonas has been a stage-hand and loader for StarRider for the past 18 months. Before that he worked for various crewing labour-hire companies, so he certainly has the experience in the field. Jonas also plays in a local band so he is likely to have some good background knowledge into the technical side of audio. Jonas has a current driver license and is often seen driving the smaller equipment trucks to and from shows. Jim Martin, Jonas' crew manager says he is very quick to pick new skills up by watching the senior production crew. He is known to sometimes act a bit too confidently without a full understanding which sometimes causes safety concerns. Jonas has confirmed he hates the “theory stuff” but loves learning by watching and working with others and also by doing. Jonas says he could probably start the corporate A/V work now without any training. Jonas holds relevant tickets for working at heights, confined spaces and has his OHS White-card. |  |  |
| External learning & monitoring arrangements | All learning is to be conducted on the job. |  |  |
| Supervisory & monitoring arrangements | Rod Logan is the senior productions manager and will be Jonas' supervisor at head office. When Jonas is out working as part of this learning pathway his immediate supervisor will be the most senior technician at the venue. Training and sharing of knowledge is built in to every staff-member's job description and each supervisor at each even will be made aware of Jonas' requirements for learning and their role in openly sharing their knowledge. |  |  |
| Resource requirements |  |  |  |

| Date/Timing | Session objective | Activity | Staff | Location |
| --- | --- | --- | --- | --- |
| 27 July 4pm - 11pm | • Set up a small A/V rig correctly, quickly and confidently • Take down a small A/V rig correctly and efficiently, ensuring a neat and tidy pack-up • Load the van correctly and safely and drive to and from the venue | Observe and assist technician in loading, setting up and taking down and packing equipment into the van for an awards night. Jonas to observe the technician during | Billy Parker (A/V tech) | Job commence and complete at StarRider head office, job is on location at venue |
| 28 July 3pm - late |  | Observe and assist technician in loading, setting up and taking down and packing equipment into the van for a family reunion private function. Jonas to observe the technician during operation and assist where needed. | Billy Parker (A/V tech) | Job commence and complete at StarRider head office, job is on location at venue |
| 29 July 12pm – 10pm |  | Observe and assist technician in loading, setting up and taking down and packing equipment into the van for a product launch. Jonas to observe the technician during operation and assist where needed. | Simone Milford (A/V tech) | Job commence and complete at StarRider head office, job is on location at venue |
| 1 August 9am - 10am | • Check progress • Debrief learning so far • Formative assessment | Jonas and Marcelle meeting | Marcelle Wyatt, Billy Parker | StarRider head office |
| 3 August 10am - 3pm | • Set up a small A/V rig correctly, quickly and confidently • Operate the equipment correctly • Take down a small A/V rig correctly and efficiently, ensuring a neat and tidy pack-up • Load the van correctly and safely and drive to and from the venue | Jonas to lead the loading, setting up and taking down and packing equipment operations and will be assisted by the technician for a Senior Citizens' function at a local bowling club. Technician to conduct sound check and ensure all equipment is operational. Jonas to operate the equipment under close supervision of technician who is to intervene should there be any issues. | Craig Tomlinson (A/V tech) | Job commence and complete at StarRider head office, job is on location at venue |
| 4 August 9am - 10am | • Check progress • Debrief learning so far • Formative assessment • Confirm satisfactory performance in previous job | Jonas and Marcelle meeting | Marcelle Wyatt, Craig Tomlinson | StarRider head office |
| 6 August – 7 August full days | • Set up a small A/V rig correctly, quickly and confidently • Operate the equipment correctly • Take down a small A/V rig correctly and efficiently, ensuring a neat and tidy pack-up • Load the van correctly and safely and drive to and from the venue | Jonas to lead the loading, setting up and taking down and packing equipment operations and will be assisted by the technician for a Wedding Technician to conduct sound check and ensure all equipment is operational. Jonas to operate the equipment under close supervision of technician who is to | Simone Milford (A/V tech) | Job commence and complete at StarRider head office, job is on location at venue. Note, venue is about 350km away so accommodation is provided.. |
| through to Monday 29 August. |  | Jonas to continue leading the load, setup, take-down and packing process assisted by another A/V tech. Jonas to take on increased responsibility for operating equipment under technician's supervision. This is to continue for as many suitable events as possible through to Monday 29 August. | A/V Technicians responsible for the show | StarRider head office and various venues as required. |
| 29 August 9am - 10am | • Check progress • Debrief learning so far • Formative assessment • Confirm satisfactory performance to date and readiness to work entire job. | Jonas to lead the operations for an entire show without intervention from senior technician. They will of course act as an assistant. | Marcelle Wyatt and one of the A/V techs who most recently worked with Jonas on an event | StarRider head office |
| All scheduled events between 30 August – 2 September | • Set up a small A/V rig correctly, quickly and confidently • Operate the equipment correctly • Take down a small A/V rig correctly and efficiently, ensuring a neat and tidy pack-up • Load the van correctly and safely and drive to and from the venue • Be confident, polite, professional and courteous to clients and dress appropriately | Jonas and Marcelle meeting | Available A/V tech | StarRider head office and various venues as required. |
| 5 September 9am - 10am | • Check progress • Debrief learning so far • Summative assessment • Confirm satisfactory performance to date • Confirm readiness to work entire shows as A/V technition assisted by junior support staff. | Jonas, Marcelle and Rod Logan to meet to confirm the outcomes of the learning pathway and review. Rod to consider implementing further similar pathways if successful. | Marcelle Wyatt and one of the A/V techs who most recently worked with Jonas on an event. | StarRider head office. |
| 9 September | • Review process |  | Jonas, Marcelle and Rod Logan | StarRider head office. |

| Supervisor signature | Real signature required | Date | 20/07/XX |
| --- | --- | --- | --- |
| Learner signature | Real signature required | Date | 20/07/XX |
| Facilitator signature | Real signature required | Date | 20/07/XX |